## Slide 1
AFRICA CLIMATE LEADERSHIP ACADEMY
Results-Based M&E: Monitoring & Evaluation
Theory of change, indicators, data quality, evaluation designs and adaptive management — the complete M&E professional skillset.…
Advanced
8 modules
41 lessons
Dr. Halima Suleiman · 10 weeks · Certificate included
ACLA.IO · TAPI LEARN
Notes: Welcome to Results-Based M&E: Monitoring & Evaluation, an Africa Climate Leadership Academy course. This presentation walks you through the whole course. Your instructor is Dr. Halima Suleiman. (8 modules, 41 lessons.)

## Slide 2
ABOUT THIS COURSE
Why this course matters
Results-Based M&E: Monitoring & Evaluation trains the discipline that every serious programme needs. Eight modules cover results-based management and the results chain, the distinct purposes of monitoring and evaluation, building theories of change and results frameworks, choosing indicators and setting baselines and targets, designing the M&E plan, data collection methods, data quality assurance and analysis, evaluation approaches, reporting and adaptive management, plus ethics, inclusion and a capstone M&E design.
8
Modules
41
Deep lessons
60% / 80%
Quiz / final pass marks
PDF
Certificate on pass
Study guide PDF & these slides are free at acla.io/courses
Notes: Results-Based M&E: Monitoring & Evaluation trains the discipline that every serious programme needs. Eight modules cover results-based management and the results chain, the distinct purposes of monitoring and evaluation, building theories of change and results frameworks, choosing indicators and setting baselines and targets, designing the M&E plan, data collection methods, data quality assurance and analysis, evaluation approaches, reporting and adaptive management, plus ethics, inclusion and a capstone M&E design. It is the deepest technical course in the Tapi Learn catalogue.

## Slide 3
LEARNING OUTCOMES
What you will be able to do
1
Define Results-Based Management (RBM) and explain why it emerged.
2
Distinguish RBM from traditional, activity-based project management.
3
Explain the results chain: inputs, activities, outputs, outcomes, and impact.
4
Identify the core principles that make an M&E system 'results-based'.
5
Define monitoring and evaluation and explain how they differ and complement each other.
6
Identify the main types of monitoring and evaluation used in project management.
7
Explain the purposes M&E serves for different stakeholders.
8
Describe the M&E cycle and its relationship to the project cycle.
Notes: By the end of this course you will be able to: Define Results-Based Management (RBM) and explain why it emerged. Distinguish RBM from traditional, activity-based project management. Explain the results chain: inputs, activities, outputs, outcomes, and impact. Identify the core principles that make an M&E system 'results-based'. Define monitoring and evaluation and explain how they differ and complement each other. Identify the main types of monitoring and evaluation used in project management. Explain the purposes M&E serves for different stakeholders. Describe the M&E cycle and its relationship to the project cycle.

## Slide 4
COURSE MAP
Your learning journey
01
Foundations of Results-Based Management
4 lessons · 8m
02
Introduction to Monitoring and Evaluation
5 lessons · 10m
03
Theory of Change and Results Frameworks
3 lessons · 6m
04
Indicators, Baselines and Targets
6 lessons · 12m
05
The M&E Plan and Data Collection
6 lessons · 14m
06
Data Quality, Management and Analysis
5 lessons · 10m
07
Evaluation, Reporting and M&E Systems
6 lessons · 20m
08
Ethics, Inclusion and the Capstone
6 lessons · 12m
Notes: Here is your learning journey. We will move through Foundations of Results-Based Management, then Introduction to Monitoring and Evaluation, then Theory of Change and Results Frameworks, then Indicators, Baselines and Targets, then The M&E Plan and Data Collection, then Data Quality, Management and Analysis, then Evaluation, Reporting and M&E Systems, then Ethics, Inclusion and the Capstone.

## Slide 5
MODULE 01 · 4 LESSONS
Foundations of Results-Based Management
RBM shifts the central management question from 'did we do the work?' to 'did the intended change happen?' The results chain — inputs, activities, outputs, outcomes, impact — is the basic causal logic underlying all RBM tools.
Notes: Module 1: Foundations of Results-Based Management. RBM shifts the central management question from 'did we do the work?' to 'did the intended change happen?' The results chain — inputs, activities, outputs, outcomes, impact — is the basic causal logic underlying all RBM tools. Confidence in causal attribution weakens as you move up the results chain, because more external factors intervene. RBM is only as good as its use: data that is collected bu

## Slide 6
MODULE 01
Lessons in this module
▤
What Is Results-Based Management?
10 min
▤
Traditional vs. Results-Based Management
9 min
▤
The Results Chain
10 min
▤
Core Principles of Results-Based Management
12 min
Notes: This module covers: What Is Results-Based Management?; Traditional vs. Results-Based Management; The Results Chain; Core Principles of Results-Based Management.

## Slide 7
MODULE 01 · KEY TAKEAWAYS
What to remember
✓
Results-Based Management transforms how organizations plan, implement, and evaluate by shifting focus from activities to measurable outcomes.
What Is Results-Based Management?
✓
Results-based management shifts focus from measuring activities to measuring actual changes in conditions or behaviors.
Traditional vs. Results-Based Management
✓
A well-constructed results chain transforms abstract intentions into measurable pathways of change
The Results Chain
✓
Results-Based Management requires defining clear, measurable outcomes before implementation begins, not afterward.
Core Principles of Results-Based Management
Notes: Key points to remember from this module.

## Slide 8
“
"Without measuring results, we're just guessing about impact—and guesswork has no place in climate adaptation programming."
What Is Results-Based Management? · Module 1
Notes: A core idea from this module: "Without measuring results, we're just guessing about impact—and guesswork has no place in climate adaptation programming."

## Slide 9
MODULE 02 · 5 LESSONS
Introduction to Monitoring and Evaluation
Monitoring is continuous and descriptive ('what is happening'); evaluation is periodic and analytical ('why, and so what'). M&E serves four purposes at once: accountability, learning, management decision-making, and beneficiary empowerment. M&E should be embedded across the whole project cycle, not treated as an end-of-project activity.
Notes: Module 2: Introduction to Monitoring and Evaluation. Monitoring is continuous and descriptive ('what is happening'); evaluation is periodic and analytical ('why, and so what'). M&E serves four purposes at once: accountability, learning, management decision-making, and beneficiary empowerment. M&E should be embedded across the whole project cycle, not treated as an end-of-project activity. Good M&E design combines multiple monitoring types (results,

## Slide 10
MODULE 02
Lessons in this module
▤
Defining Monitoring and Evaluation
11 min
▤
Types of Monitoring
14 min
▤
Types of Evaluation
10 min
▤
Why M&E Matters: Four Purposes
15 min
▤
The M&E Cycle and the Project Cycle
13 min
Notes: This module covers: Defining Monitoring and Evaluation; Types of Monitoring; Types of Evaluation; Why M&E Matters: Four Purposes; The M&E Cycle and the Project Cycle.

## Slide 11
MODULE 02 · KEY TAKEAWAYS
What to remember
✓
Monitoring tracks progress against plans while evaluation assesses why results occurred or not.
Defining Monitoring and Evaluation
✓
Results monitoring focuses on outcomes and outputs, providing evidence of whether a project is achieving its intended impact.
Types of Monitoring
✓
Different evaluation types serve distinct purposes throughout the project lifecycle and must be carefully selected based on decision-making needs.
Types of Evaluation
✓
Effective M&E systems must simultaneously serve accountability, learning, management, and empowerment purposes to maximize development impact.
Why M&E Matters: Four Purposes
✓
Effective M&E must be systematically integrated throughout the entire project cycle, not treated as a separate activity.
The M&E Cycle and the Project Cycle
Notes: Key points to remember from this module.

## Slide 12
“
"Without measurement, we are just another voice in the dark; without evaluation, we are just counting beans without understanding why they matter."
Defining Monitoring and Evaluation · Module 2
Notes: A core idea from this module: "Without measurement, we are just another voice in the dark; without evaluation, we are just counting beans without understanding why they matter."

## Slide 13
MODULE 03 · 3 LESSONS
Theory of Change and Results Frameworks
A theory of change makes explicit the causal logic and assumptions behind a project — not just what will happen, but why and under what conditions. Assumptions and risks identified in the theory of change should become part of what the M&E system tracks, not an afterthought.
Notes: Module 3: Theory of Change and Results Frameworks. A theory of change makes explicit the causal logic and assumptions behind a project — not just what will happen, but why and under what conditions. Assumptions and risks identified in the theory of change should become part of what the M&E system tracks, not an afterthought. A results framework operationalizes the theory of change into a structured table of results, indicators, baselines, targets,

## Slide 14
MODULE 03
Lessons in this module
▤
What Is a Theory of Change?
10 min
▤
From Theory of Change to Results Framework
10 min
▤
Common Pitfalls in Theory of Change and Results Framework Design
11 min
Notes: This module covers: What Is a Theory of Change?; From Theory of Change to Results Framework; Common Pitfalls in Theory of Change and Results Framework Design.

## Slide 15
MODULE 03 · KEY TAKEAWAYS
What to remember
✓
A Theory of Change is not just a diagram but an evidence-based narrative explaining why and how change will occur in your specific context.
What Is a Theory of Change?
✓
A results framework transforms theoretical pathways into measurable outcomes through a hierarchical structure of indicators and targets.
From Theory of Change to Results Framework
✓
Distinguishing clearly between outputs and outcomes is fundamental to measuring real impact rather than just activity.
Common Pitfalls in Theory of Change and Results Framework Design
Notes: Key points to remember from this module.

## Slide 16
MODULE 04 · 6 LESSONS
Indicators, Baselines and Targets
SMART and CREAM are complementary checklists for indicator quality; use both to stress-test proposed indicators. Proxy indicators are sometimes necessary but must be used with an explicit, periodically revisited justification for the correlation assumed.
Notes: Module 4: Indicators, Baselines and Targets. SMART and CREAM are complementary checklists for indicator quality; use both to stress-test proposed indicators. Proxy indicators are sometimes necessary but must be used with an explicit, periodically revisited justification for the correlation assumed. A credible baseline, collected using the same method as future rounds, is a precondition for any credible claim about project results. Disaggrega

## Slide 17
MODULE 04
Lessons in this module
▤
What Is an Indicator?
11 min
▤
Criteria for Good Indicators: SMART and CREAM
13 min
▤
Types of Indicators
12 min
▤
Baselines
12 min
▤
Setting Targets
10 min
▤
Disaggregation for Equity-Sensitive Monitoring
12 min
Notes: This module covers: What Is an Indicator?; Criteria for Good Indicators: SMART and CREAM; Types of Indicators; Baselines; Setting Targets; Disaggregation for Equity-Sensitive Monitoring.

## Slide 18
MODULE 04 · KEY TAKEAWAYS
What to remember
✓
Well-designed indicators are the cornerstone of effective climate program M&E, providing objective evidence of progress toward intended outcomes.
What Is an Indicator?
✓
Well-designed climate indicators bridge the gap between climate action and measurable impact, enabling evidence-based decision-making in resource-c…
Criteria for Good Indicators: SMART and CREAM
✓
Indicator selection must align with your theory of change and specific intervention context.
Types of Indicators
✓
A credible baseline is the essential foundation for attributing changes to project interventions and avoiding false claims of impact.
Baselines
✓
Targets must be evidence-based, drawing from baselines, trends, comparable interventions, and stakeholder input.
Setting Targets
✓
Disaggregation is essential for identifying and addressing equity gaps in climate programming across Africa.
Disaggregation for Equity-Sensitive Monitoring
Notes: Key points to remember from this module.

## Slide 19
MODULE 05 · 6 LESSONS
The M&E Plan and Data Collection
The M&E plan operationalizes the results framework: it specifies how, by whom, how often, and at what cost data will be collected, analyzed, and used. The Performance Indicator Tracking Table (PITT) is the master reference document at the centre of the M&E plan.
Notes: Module 5: The M&E Plan and Data Collection. The M&E plan operationalizes the results framework: it specifies how, by whom, how often, and at what cost data will be collected, analyzed, and used. The Performance Indicator Tracking Table (PITT) is the master reference document at the centre of the M&E plan. M&E budgets should be built bottom-up from costed activities, not set as an arbitrary percentage, though 3–10% of total project cost is a

## Slide 20
MODULE 05
Lessons in this module
▤
What Is an M&E Plan?
10 min
▤
Core Components of an M&E Plan
9 min
▤
Budgeting for M&E
10 min
▤
Roles and Responsibilities
9 min
▤
Quantitative Methods
11 min
▤
Sampling Essentials
12 min
Notes: This module covers: What Is an M&E Plan?; Core Components of an M&E Plan; Budgeting for M&E; Roles and Responsibilities; Quantitative Methods; Sampling Essentials.

## Slide 21
MODULE 05 · KEY TAKEAWAYS
What to remember
✓
A results-based M&E plan transforms indicators into actionable intelligence with clear specifications for data collection, analysis, and reporting.
What Is an M&E Plan?
✓
A comprehensive M&E plan transforms climate interventions from aspirational goals into measurable, accountable actions with clear pathways for adap…
Core Components of an M&E Plan
✓
M&E budgeting should be driven by verification needs, not arbitrary percentages, with climate projects typically requiring 7-12% for adequate monit…
Budgeting for M&E
✓
Clearly defined roles and responsibilities prevent data from being collected in a vacuum and ensure findings inform decision-making.
Roles and Responsibilities
✓
Quantitative methods must be purposefully selected based on evaluation questions, resource constraints, and data quality requirements.
Quantitative Methods
✓
A flawed sampling frame guarantees flawed results, regardless of perfect questionnaire design or analysis.
Sampling Essentials
Notes: Key points to remember from this module.

## Slide 22
MODULE 06 · 5 LESSONS
Data Quality, Management and Analysis
The five dimensions of data quality — validity, reliability, timeliness, precision, and integrity — provide a practical checklist for assessing any indicator's data.
Notes: Module 6: Data Quality, Management and Analysis. The five dimensions of data quality — validity, reliability, timeliness, precision, and integrity — provide a practical checklist for assessing any indicator's data. Data quality assurance is a management responsibility, not solely a technical or clerical one; poor data quality creates false confidence, which is more dangerous than an acknowledged data gap. Data quality audits (DQAs) are a standar

## Slide 23
MODULE 06
Lessons in this module
▤
Why Data Quality Is a Management Issue, Not Just a Technical One
10 min
▤
The Five Dimensions of Data Quality
14 min
▤
Data Quality Assurance Mechanisms
12 min
▤
Managing Data Across Its Lifecycle
13 min
▤
Basic Data Analysis for M&E Practitioners
11 min
Notes: This module covers: Why Data Quality Is a Management Issue, Not Just a Technical One; The Five Dimensions of Data Quality; Data Quality Assurance Mechanisms; Managing Data Across Its Lifecycle; Basic Data Analysis for M&E Practitioners.

## Slide 24
MODULE 06 · KEY TAKEAWAYS
What to remember
✓
Data quality is fundamentally a leadership issue requiring management commitment, not just technical solutions.
Why Data Quality Is a Management Issue, Not Just a Technical One
✓
Validity is not inherent in data but must be deliberately designed through appropriate indicator selection and measurement methods.
The Five Dimensions of Data Quality
✓
Data quality is not a one-time check but a continuous system requiring dedicated resources and clear accountability.
Data Quality Assurance Mechanisms
✓
Effective data management transforms climate information into actionable insights that drive evidence-based decision-making across African contexts.
Managing Data Across Its Lifecycle
✓
Effective M&E analysis transforms raw data into actionable insights through systematic descriptive statistics, trend analysis, and disaggregation.
Basic Data Analysis for M&E Practitioners
Notes: Key points to remember from this module.

## Slide 25
MODULE 07 · 6 LESSONS
Evaluation, Reporting and M&E Systems
The OECD-DAC criteria — relevance, coherence, effectiveness, efficiency, impact, sustainability — provide a common structure for framing evaluation questions. The counterfactual problem — we cannot observe what would have happened without the project — is the central technical challenge of impact attribution.
Notes: Module 7: Evaluation, Reporting and M&E Systems. The OECD-DAC criteria — relevance, coherence, effectiveness, efficiency, impact, sustainability — provide a common structure for framing evaluation questions. The counterfactual problem — we cannot observe what would have happened without the project — is the central technical challenge of impact attribution. Experimental (RCT), quasi-experimental, and theory-based designs each construct or approx

## Slide 26
MODULE 07
Lessons in this module
▤
The OECD-DAC Evaluation Criteria
12 min
▤
Evaluation Designs
4 min
▤
Choosing an Evaluation Design
12 min
▤
Adaptive Management: Using M&E to Steer, Not Just to Score
11 min
▤
Barriers to Using M&E Findings — and How to Address Them
10 min
▤
Assessing M&E System Maturity
5 min
Notes: This module covers: The OECD-DAC Evaluation Criteria; Evaluation Designs; Choosing an Evaluation Design; Adaptive Management: Using M&E to Steer, Not Just to Score; Barriers to Using M&E Findings — and How to Address Them; Assessing M&E System Maturity.

## Slide 27
MODULE 07 · KEY TAKEAWAYS
What to remember
✓
The OECD-DAC criteria provide a comprehensive framework for evaluating climate interventions, with each criterion addressing a distinct dimension o…
The OECD-DAC Evaluation Criteria
✓
Evaluation design must be purpose-driven, not method-driven, with careful consideration of feasibility and ethical implications
Choosing an Evaluation Design
✓
Adaptive management transforms M&E from a retrospective accountability tool to a forward-looking strategic function.
Adaptive Management: Using M&E to Steer, Not Just to Score
✓
Addressing barriers to M&E utilization requires deliberate organizational change beyond technical fixes.
Barriers to Using M&E Findings — and How to Address Them
Notes: Key points to remember from this module.

## Slide 28
MODULE 08 · 6 LESSONS
Ethics, Inclusion and the Capstone
Informed consent, confidentiality, do-no-harm, and safe referral pathways are non-negotiable minimum standards for any M&E data collection, and must be planned before fieldwork, not improvised during it.
Notes: Module 8: Ethics, Inclusion and the Capstone. Informed consent, confidentiality, do-no-harm, and safe referral pathways are non-negotiable minimum standards for any M&E data collection, and must be planned before fieldwork, not improvised during it. Participatory M&E treats beneficiaries as active participants in defining, collecting, and interpreting results — not only as data sources. Extractive data practices — repeated data collection wit

## Slide 29
MODULE 08
Lessons in this module
▤
Core Ethical Principles in M&E
13 min
▤
Participatory and Beneficiary-Centred M&E
13 min
▤
Guarding Against Extractive Data Practices
10 min
▤
Gender-Responsive and Disability-Inclusive M&E
11 min
▤
Capstone Deliverables
10 min
▤
Certification
9 min
Notes: This module covers: Core Ethical Principles in M&E; Participatory and Beneficiary-Centred M&E; Guarding Against Extractive Data Practices; Gender-Responsive and Disability-Inclusive M&E; Capstone Deliverables; Certification.

## Slide 30
MODULE 08 · KEY TAKEAWAYS
What to remember
✓
Ethical M&E requires continuous engagement and adaptation, not just compliance with minimum standards.
Core Ethical Principles in M&E
✓
Participatory M&E transforms beneficiaries from data subjects to knowledge co-producers, yielding more relevant and sustainable climate interventions.
Participatory and Beneficiary-Centred M&E
✓
Extractive data practices undermine climate action effectiveness by eroding community trust and compromising data quality.
Guarding Against Extractive Data Practices
✓
Gender-responsive and disability-inclusive M reveals hidden inequities and improves program effectiveness for all beneficiaries.
Gender-Responsive and Disability-Inclusive M&E
✓
Capstone deliverables must demonstrate both technical M&E expertise and contextual relevance to African development challenges.
Capstone Deliverables
✓
Certification in Results-Based M&E validates your ability to design and implement rigorous M systems that demonstrate climate intervention impact.
Certification
Notes: Key points to remember from this module.

## Slide 31
ASSESSMENT & CERTIFICATE
Prove what you know
✦
Module quizzes
After every module — pass at 60% to complete it. Explanations after every question make wrong answers a learning tool.
♛
Final test & certificate
Pass at 80% to earn the official ACLA certificate — signed, PDF-downloadable and verifiable online at acla.io/verify.
XP REWARDS
Lesson completed
+10 XP
Module quiz passed
+50 XP
Final test passed
+150 XP
Certificate earned
+100 XP
Cloud backup keeps all progress safe under your email.
Notes: Every module ends with a quiz — 60% to pass, with explanations for every answer. The final test needs 80%, and passing earns your verified ACLA certificate, downloadable as a PDF and verifiable at acla.io/verify. XP rewards keep you motivated.

## Slide 32
YOUR TURN
Start learning today —
it's completely free
Take the full course — 41 lessons, quizzes and your verified certificate — in the Tapi Learn app, or read the complete study guide PDF at acla.io/courses.
Download Tapi Learn — acla.io/tapi-learn
Study guide — acla.io/courses
AFRICA CLIMATE LEADERSHIP ACADEMY
Notes: Start learning today — the course is completely free in the Tapi Learn app, and the full study guide PDF is at acla.io/courses. Good luck!